## Open POA&M Items
Plan of Action and Milestones — Kubernetes Cluster (k8s-prod)
Instructions: fill open POA&M items below. Row 5 = headers, row 6+ = data.
POAM ID | Controls | Weakness Name | Weakness Description | Weakness Detector Source | CVE | Point of Contact | Original Risk Rating | Scheduled Completion Date | Planned Milestones
P-001 | AC-2 | MFA not enforced on admin accounts | 3 cluster-admin accounts can authenticate without MFA. | Kube-bench |  | Platform Security Team | High | 2026-12-31 | Enable MFA policy in IdP by 2026-10-01
P-002 | AU-2 | API server audit logging disabled | kube-apiserver started without --audit-policy-file. | Kube-bench |  | Platform Team | Moderate | 2026-11-30 | Deploy audit policy by 2026-11-01